## Project Overview
brief description of the project
purpose
goals
target audience
Explain the need for an online presence

## GanttChart
WheelPact - Project Schedule
Company Name
| Project Start Date | 2023-06-05 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14
| Project Lead | Sai Atpadkar, Santosh Paskanti | [6 empty] | 2023-06-05 | [6 empty] | 2023-06-12 | [6 empty] | 2023-06-19 | [6 empty] | 2023-06-26 | [6 empty] | 2023-07-03 | [6 empty] | 2023-07-10 | [6 empty] | 2023-07-17 | [6 empty] | 2023-07-24 | [6 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04
 | time axis 2023-06-05 to 2023-09-10
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2023-06-05 to 2023-09-10
1 | Super Admin |  |  |  | - |  |  | -
1.1 | SuperAdmin Template Setup |  |  | 2023-06-06 | 2023-06-08 | 3 | 0% | 3
1.2 | SuperAdmin Login,Logout,Profile,Change Password |  |  | 2023-06-09 | 2023-06-11 | 3 | 0% | 1
1.3 | Dealers |  |  | 2023-06-12 | 2023-06-26 | 15 | 10% | 11
1.3.1 | Add Dealer |  |  | 2023-05-29 | 2023-06-02 | 5 | 15% | 5
1.3.2 | View Dealers |  |  | 2023-05-29 | 2023-05-30 | 2 | 10% | 2
1.4 | Manage Vehicles |  |  | 2023-06-07 | 2023-06-09 | 3 | 0% | 3
1.4.1 | Add Vehicle |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
1.4.2 | View Vehicles |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
1.5 | Email Subscribers |  |  | 2023-06-05 | 2023-06-06 | 2 | 0% | 2
1.5.1 | View All Subscribers |  |  | 2023-06-05 | 2023-06-05 | 1 | 5% | 1
1.6 | Support Tickets |  |  | 2023-06-07 | 2023-06-09 | 3 | 0% | 3
1.6.1 | View All Tickets |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
1.7 | Manage Reports |  |  | 2023-06-07 | 2023-06-09 | 3 | 0% | 3
1.7.1 | reports types |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
2 | Dealer |  |  |  | - |  |  | -
2.1 | Dealer Template Setup |  |  | 2023-06-07 | 2023-06-09 | 3 | 0% | 3
2.2 | Login, Logout, Forgot Password, Change Password,Profile |  |  | 2023-06-07 | 2023-06-09 | 3 | 0% | 3
2.3 | Manage Vehicles |  |  | 2023-06-07 | 2023-06-09 | 3 | 0% | 3
2.3.1 | Add Vehicle |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
2.3.2 | View Vehicles |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
2.4 | Manage Promotions |  |  | 2023-06-07 | 2023-06-09 | 3 | 0% | 3
2.4.1 | Add Promotion |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
2.4.2 | View Promotions |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
2.5 | Manage Branches |  |  | 2023-06-07 | 2023-06-09 | 3 | 0% | 3
2.5.1 | Add Branch |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
2.5.2 | View Branches |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
2.6 | Manage Reservations |  |  | 2023-06-07 | 2023-06-09 | 3 | 0% | 3
2.6.1 | View Reservations |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
2.7 | Mobile App |  |  | 2023-06-07 | 2023-06-09 | 3 | 0% | 3
2.7.1 | Android |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
2.7.2 | IOS |  |  | 2023-06-07 | 2023-06-07 | 1 | 5% | 1
1 | Customer |  |  |  | - |  |  | -
1.1 | Search Vehicles |  |  | 2023-07-14 | 2023-08-12 | 30 | 0% | 21
1.2 | Wishlist Vehicle |  |  | 2023-07-14 | 2023-08-12 | 30 | 0% | 21
1.3 | Reserve Vehicle |  |  | 2023-07-14 | 2023-08-12 | 30 | 0% | 21
Showroom Promotion List
0.1 | Mobile App |  |  | 2023-07-14 | 2023-08-12 | 30 | 0% | 21
0.1.1 | Android |  |  | 2023-07-14 | 2023-07-28 | 15 | 5% | 11
0.1.2 | IOS |  |  | 2023-08-01 | 2023-08-15 | 15 | 5% | 11
1 | API Develoment & Integration |  |  |  | - |  |  | -
1.1 | Super Admin Login |  |  | 2023-08-16 | 2023-08-30 | 15 | 0% | 11
1.2 | Dealer Login |  |  | 2023-08-16 | 2023-08-16 | 1 | 0% | 1
1.3 | Customer Login |  |  | 2023-08-17 | 2023-08-17 | 1 | 0% | 1
1.4 | Vehicle List |  |  | 2023-08-18 | 2023-08-18 | 1 | 0% | 1
1.5 | Showroom List |  |  | 2023-08-18 | 2023-08-18 | 1 | 0% | 1
2 | Website (Open to Public) |  |  |  | - |  |  | -
2.1 | Website (Open to Public) |  |  | 2023-06-12 | 2023-06-13 | 2 | 0% | 2
2.1.1 | Vehicle Listing |  |  | 2023-06-12 | 2023-06-12 | 1 | 5% | 1
2.1.2 | Showroom Listing |  |  | 2023-06-12 | 2023-06-12 | 1 | 5% | 1
2.1.3 | Contact Us |  |  | 2023-06-13 | 2023-06-13 | 1 | 5% | 1
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## Resources
Sr. No | Role | No. Of Resource Required
1 | Flutter Dart Developer | 1
2 | Backend Developer (API) | 1
3 | Project Manager / Co-ordinator / Scrum Master | 1
4 | UI - UX / Front End Developer | 1

## Module List
SuperAdmin
Super Admin Login&Logout
Dashboard
Dealers
Add Dealer
View Dealers
Vehicle Types
Cars
Sedans, Hatchbacks, SUVs/Crossovers, Coupes, Convertibles, Sports Cars , Luxury Cars, Electric/Hybrid Cars, Vintage/Classic Cars
Bikes
Motorcycles, Scooters, Sports Bikes, Cruisers, Off-road/Adventure Bikes, Electric Bikes, Commuter Bikes, Vintage/Classic Bikes
Vehicles Ownership Type
1st Owner, 2nd Owner, Subsequent Owner,etc.
Email Subscribers
Support Tickets
Manage Reports
Dealer
Dealer Login&Logout
Dashboard
Showrooms
Add Branch
Name
Type
Address
Contact
View Branches
Vehicles
Add Vehicles
View Vehicles
Customer

## Database Schema
1. Collection: Users
_id: Unique identifier for the user.
name: User's name.
email: User's email address.
password: User's hashed password.
contact_number: User's contact number.
address: User's address details.
created_at: Timestamp for when the user account was created.
updated_at: Timestamp for when the user account was last updated.
2. Collection: Vehicles
_id: Unique identifier for the vehicle.
manufacturer_id: ID of the model (reference to the Manufacturers collection).
model_id: ID of the model (reference to the Models collection).
year: Vehicle's manufacturing year.
type: Vehicle's type (car, bike, van, etc.).
price: Vehicle's price.
mileage: Vehicle's mileage.
condition: Vehicle's condition (e.g., new, used, refurbished).
owner_id: ID of the user who owns the vehicle (reference to Users collection).
location: Vehicle's location.
features: Array of additional features or specifications of the vehicle.
images: Array of image URLs representing the vehicle.
created_at: Timestamp for when the vehicle was added to the database.
updated_at: Timestamp for when the vehicle information was last updated.
3. Collection: Transactions
_id: Unique identifier for the transaction.
vehicle_id: ID of the vehicle involved in the transaction (reference to Vehicles collection).
buyer_id: ID of the buyer involved in the transaction (reference to Users collection).
seller_id: ID of the seller involved in the transaction (reference to Users collection).
transaction_date: Date of the transaction.
transaction_amount: Amount of the transaction.
payment_method: Payment method used for the transaction.
created_at: Timestamp for when the transaction was recorded.
4. Collection: Reviews
_id: Unique identifier for the review.
vehicle_id: ID of the vehicle being reviewed (reference to Vehicles collection).
user_id: ID of the user who posted the review (reference to Users collection).
rating: Rating given by the user for the vehicle.
comment: User's comment or feedback.
created_at: Timestamp for when the review was posted.
5. Collection: Favorites
_id: Unique identifier for the favorite item.
user_id: ID of the user who favorited the vehicle (reference to Users collection).
vehicle_id: ID of the favorited vehicle (reference to Vehicles collection).
created_at: Timestamp for when the favorite was added.
6. Collection: Manufacturers
_id: Unique identifier for the manufacturer.
name: Manufacturer's name.Vehicle's make (e.g., Honda, Toyota, BMW).
country: Country of origin for the manufacturer.
logo: URL or path to the manufacturer's logo.
created_at: Timestamp for when the manufacturer record was created.
updated_at: Timestamp for when the manufacturer record was last updated.
7. Collection: Models
_id: Unique identifier for the model.
manufacturer_id: ID of the manufacturer (reference to the Manufacturers collection).
name: Model's name.
segment: Vehicle segment to which the model belongs (e.g., Sedan, SUV, Hatchback).
fuel_type: Type of fuel the model runs on (e.g., Petrol, Diesel, Electric).
created_at: Timestamp for when the model record was created.
updated_at: Timestamp for when the model record was last updated.