## Gantt Chart
Reservation System Project Plan
PROJECT TITLE |  | WheelPact |  |  |  |  | COMPANY NAME | [6 empty] | WheelPact
PROJECT MANAGER |  | Santosh Paskanti |  |  |  |  | DATE | [6 empty] | 2022-12-16
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (DAYS) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Initiation
1.1 | Evaluation of Idea | bar: WEEK 1 W to WEEK 2 R; WEEK 5 T; WEEK 11 M
1.1.1 | Assessing Business Idea | bar: WEEK 2 T; WEEK 5 T; WEEK 11 M
1.2 | Gathering Team Members | bar: WEEK 2 T to WEEK 2 R; WEEK 5 T; WEEK 11 M
1.3 | Assigning Roles as per Skills | bar: WEEK 2 R to WEEK 2 F; WEEK 5 T; WEEK 11 M
1.4 | Meeting for Discussing Finances | bar: WEEK 3 M; WEEK 5 T; WEEK 11 M
1.4 | Monthly meeting to map progress. | bar: WEEK 3 T to WEEK 3 F; WEEK 5 T; WEEK 11 M
2 | Sourcing
2.1 | Choose a Stack to develop on | bar: WEEK 4 W to WEEK 5 T; WEEK 11 M
2.2 | Hosting Services | bar: WEEK 4 F to WEEK 5 T; WEEK 11 M
2.3 | Domain Registration | bar: WEEK 4 F to WEEK 5 W; WEEK 11 M
2.4 | Google Play and Apple App Store Developer Subscription | bar: WEEK 5 T to WEEK 5 F; WEEK 11 M
2.5 | Company Registration and TradeMark | bar: WEEK 5 T to WEEK 5 F; WEEK 11 M
3 | Planning
3.1 | Figure out Investment Estimation based on Project Sourcing | bar: WEEK 5 T; WEEK 6 W to WEEK 6 F; WEEK 11 M
3.2.1 | Select Development Cycle and Methodology | bar: WEEK 5 T; WEEK 7 T; WEEK 11 M
3.3 | Figure out development period estimation | bar: WEEK 5 T; WEEK 7 M to WEEK 9 F; WEEK 11 M
3.4 | Generate Weekly Progress Report | bar: WEEK 5 T; WEEK 7 R to WEEK 9 W; WEEK 11 M
4 | Development
4.1 | User End Portal | Sultan | bar: WEEK 5 T; WEEK 10 T to WEEK 10 W; WEEK 11 M
4.2 | Dealer Admin Portal | Sultan | bar: WEEK 5 T; WEEK 10 R; WEEK 11 M
4.3 | User End Mobile App | Aman | bar: WEEK 5 T; WEEK 10 F to WEEK 11 M
4.4 | Dealer End Mobile App | Aman | bar: WEEK 5 T; WEEK 11 M
4.5 | DataBase Structure | Aman | bar: WEEK 5 T; WEEK 10 T to WEEK 11 M
4.6 | Backend App development | Santosh | bar: WEEK 5 T; WEEK 11 M; WEEK 12 F
4.7 | User End Portal Content | TBD | bar: WEEK 5 T; WEEK 11 M; WEEK 12 F